## Checklist
ERP Data Migration Checklist
A step-by-step way to move your masters, balances and history into a new ERP — reconciled to the rupee, with nothing lost along the way.
Data migration is where most ERP go-lives are won or lost — a clean system built on messy, unreconciled data still gives you wrong numbers on day one. The goal isn't just to move records across; it's to move the right data, cleaned, mapped and reconciled so opening balances tie back to your trial balance and outstanding AR/AP to the rupee. Work through this checklist in order and treat reconciliation as the finish line, not an afterthought.
Item | Why it matters
AUDIT & INVENTORY THE DATA
List every data source | Old ERP, Tally, spreadsheets, portals, bank statements — write down everywhere your data actually lives.
Catalogue what data exists | Masters (customers, suppliers, items, chart of accounts) and transactions (invoices, payments, stock, GST).
Name the system of record for each | For every data set, decide which source is the master — so you never migrate two conflicting versions.
Note volumes and formats | How many records, and whether they export cleanly to CSV/Excel — this shapes your effort and timeline.
DECIDE WHAT TO MIGRATE
Masters first, always | Customers, suppliers, items, chart of accounts and tax setup are non-negotiable — everything else builds on them.
Clean start vs full history | Decide whether to bring opening balances only, or years of past transactions — more history means more cleansing and risk.
Set a cut-off date | Pick a clear go-live date; transactions before it become opening balances, transactions after it are entered live.
Agree what you will NOT migrate | Dead customers, obsolete items and stale data are best archived outside the ERP, not carried in.
CLEANSE & DE-DUPLICATE
Remove duplicates | The same customer or item entered twice becomes two ledgers in ERP — merge before you migrate, not after.
Fix errors and gaps | Missing GSTINs, blank contact details, wrong opening quantities — correct them at source while it's still easy.
Standardise formats | One convention for names, codes, states, units of measure and date formats so records match and group correctly.
Validate tax identifiers | Check GSTIN, PAN and HSN/SAC codes are present and well-formed so GST works from day one.
MAP & PREPARE
Map each field to the ERP structure | Decide where every old column lands in the new system — and flag anything with no home before you import.
Use the ERP's import templates | In ERPNext, export the Data Import template for each doctype and fill your cleaned data into it exactly.
Configure tax and GST first | Set up tax templates, HSN/SAC and place-of-supply logic before importing, so transactions calculate correctly.
Do a small test import | Load a handful of records first to catch mapping and format errors cheaply before the full run.
MIGRATE & RECONCILE
Import masters, then balances | Load customers, suppliers, items and accounts first; then opening stock and opening financial balances.
Tie opening balances to the trial balance | Your ERP opening trial balance must match your old system to the rupee — debits and credits both.
Reconcile outstanding AR/AP | Every open customer and supplier invoice should carry over so ageing and outstanding amounts are correct.
Reconcile stock and bank | Opening stock quantities and valuations, and bank/cash balances, must agree with your physical count and statements.
VALIDATE & SIGN-OFF
Spot-check a sample of records | Pick real customers, items and invoices and confirm each one landed correctly in the ERP.
Get department users to validate | The people who use the data daily will spot what a technical check misses — let them verify their own area.
Run a short parallel period | Where practical, run old and new side by side briefly so numbers can be compared before you fully cut over.
Formal sign-off before go-live | Finance signs off that balances reconcile and data is trustworthy — the gate you don't skip.
Acube Innovations · Official ERPNext Partner · acubeinnovations.com · +91 62358 66111