## Checklist
ERP Go-Live Checklist
The final checks that turn go-live from a nervous leap into a calm, confident switch-on.
Go-live should feel like flipping a switch, not jumping off a cliff. The difference is preparation: everything tested, data reconciled, people trained, and a clear plan for the day itself and the days after. Work through this checklist before you set a date — the more of it you can confirm, the calmer go-live morning will be.
Item | Why it matters
TESTING & UAT
Functional testing is complete | Every configured process has been run end-to-end and behaves as expected.
User acceptance testing is signed off | Real users tested with real scenarios and formally agreed it's fit for purpose.
Key business scenarios are verified | Your highest-volume and highest-risk flows — sales, purchase, invoicing — all work.
Known issues are logged and triaged | Anything outstanding is documented, with a call made on fix-before vs fix-after.
DATA READY
Master data is migrated and checked | Customers, suppliers, items and accounts are loaded, clean and spot-verified.
Opening balances are in and reconciled | Trial balance, stock and outstanding AR/AP match your old system to the rupee.
The reconciliation numbers tie out | Someone from finance has confirmed the totals agree — not just 'looks about right'.
A cut-off point is agreed | You know the exact date/time the old system stops and the new one becomes the record.
PEOPLE READY
Training is complete | Every user has been trained on the tasks they'll actually do day one.
Roles and permissions are set | People can see and do what they need — and nothing they shouldn't.
Department champions are briefed | Your internal go-to people know the plan and can support their teams.
Quick reference guides are handy | Short how-to notes for common tasks reduce the day-1 flood of questions.
CUTOVER PLAN
The go-live date is agreed | A date everyone owns — ideally after a period-end, avoiding your busiest week.
The cutover sequence is written down | The ordered list of steps from 'stop old system' to 'new system live'.
Who does what is clear | Every cutover task has a named owner and a time slot — no assumptions.
Everyone is told the plan | Staff, and where relevant customers and suppliers, know what changes and when.
SUPPORT & FALLBACK
Hypercare support is on standby | Your implementation team is available and responsive for the first days/weeks.
A rollback or parallel-run plan exists | You've decided how to run both systems (or step back) if something goes wrong.
An issue log is set up | One place to capture problems, owners and status — so nothing gets lost in chat.
Escalation contacts are known | Everyone knows who to call for a blocker, and how fast to expect a response.
DAY-1 & POST GO-LIVE CHECKS
First live transactions are verified | A real sales order, purchase and payment are posted and checked start to finish.
GST and e-invoice are working | A live invoice generates the correct GST, IRN/e-invoice and e-way bill where needed.
Daily health checks are running | Someone confirms backups, integrations and key reports each day of hypercare.
A review after the first close is booked | Sit down after month-end to fix rough edges and plan the next improvements.
Acube Innovations · Official ERPNext Partner · acubeinnovations.com · +91 62358 66111