## Checklist
ERP Readiness Checklist
The questions to answer before you start an ERP project — so you begin from a position of strength, not surprises.
Most ERP projects that struggle didn't fail during the build — they were under-prepared before it. Work through this checklist before you sign anything. The more of it you can confidently answer yes to, the smoother and cheaper your implementation will be — and anything you can't yet is simply a conversation to have first.
Item | Why it matters
LEADERSHIP & GOALS
A clear business reason for ERP | You can name the specific pains — not just 'we should modernise'.
An executive sponsor | A senior leader owns the outcome and can unblock decisions.
Defined success criteria | You know what 'good' looks like — measurable outcomes, not vibes.
Realistic expectations on time and effort | Everyone understands ERP is a project, not a plug-in.
PROCESSES
Your core processes are documented (or can be) | Order-to-cash, procure-to-pay, inventory, payroll — at least in outline.
You're open to changing how you work | Willingness to adopt better standard flows rather than replicate every quirk.
Process owners are identified | Someone in each department can speak for how things actually run.
DATA
You know where your data lives | Accounts, customers, suppliers, items — and which system is the master.
Data quality is understood | You have a sense of how clean (or messy) the data to migrate is.
Opening balances can be produced | A trial balance and outstanding AR/AP you can reconcile against.
TEAM & CHANGE
A project team with time allocated | Key people have bandwidth carved out — not squeezed in around day jobs.
An internal champion per department | People who'll help their teams adopt the new system.
A plan for training | You've accepted that adoption needs real training, not a one-hour demo.
BUDGET & SCOPE
A realistic budget across the full picture | Implementation, hosting, support and internal time — not just the quote.
A phased mindset | Willingness to go live on core scope first and expand, rather than boil the ocean.
Clarity on must-haves vs nice-to-haves | You can separate what you need at go-live from what can wait.
COMPLIANCE & TECHNICAL (INDIA)
GST and statutory needs are known | GST, e-invoice, e-way bill, TDS and payroll requirements are clear.
Integration needs are listed | E-commerce, payments, banking or other apps that must connect.
A hosting preference (or openness) | Cloud for convenience or self-host for control — or happy to be advised.
Acube Innovations · Official ERPNext Partner · acubeinnovations.com · +91 62358 66111