## Checklist
ERPNext Project & Timesheet Setup Checklist
A field-by-field reference for setting up the ERPNext Projects module — project types and templates, tasks with dependencies, activity rates, and timesheets that flow through to a Sales Invoice.
The ERPNext Projects module ties planning, time tracking and billing together — a Project holds Tasks, Timesheets log billable hours against those tasks, and those hours can be pulled straight into a Sales Invoice. This is a reference to the real doctypes and fields involved, not a tracker. Read it as a map of what to configure and why each piece matters, then set up your instance in the order that fits your delivery model. Every field named below exists in the standard Projects module.
Item | Why it matters
PROJECT TYPES & TEMPLATES
Define your Project Types | The Project Type doctype (e.g. Internal, External, Retainer) categorises projects; each Project links to one via the project_type field, which makes reporting and filtering meaningful.
Create a Project for each engagement | The Project doctype carries project_name, status (Open / Completed / Cancelled), is_active, priority, expected_start_date and expected_end_date, plus the customer and company it belongs to.
Build reusable Project Templates | A Project Template holds a standard set of tasks (the tasks child table of Project Template Task) and a project_type, so recurring engagements spin up with a consistent task list.
Set template task scheduling in relative days | Template tasks use start (Begin On, in days) and duration (in days) rather than fixed dates, so the plan shifts correctly whenever the project's actual start date changes.
Link a Project to its Sales Order | The sales_order field connects delivery to what was sold; total_sales_amount is then rolled up on the Project from the linked Sales Order.
TASKS & DEPENDENCIES
Create Tasks under each Project | The Task doctype has subject, status (Open / Working / Pending Review / Overdue / Completed / Cancelled), priority and a project link; it is the unit both progress and time log against.
Model hierarchy with is_group and parent_task | Set is_group on summary tasks and point child tasks at them via parent_task — Task is a tree (nested set with lft/rgt), so you can roll work up into phases.
Set task dependencies with depends_on | The depends_on child table (Task Depends On) lists prerequisite tasks; a task can't sensibly start until the tasks it depends on are done, which drives realistic scheduling.
Estimate effort with expected_time | expected_time (Expected Time, in hours), along with exp_start_date and exp_end_date, is your baseline plan; timesheets later populate actual_time to compare against.
Use task_weight and is_milestone where it matters | task_weight feeds the Task Weight completion method; is_milestone flags key checkpoints for reporting without adding effort.
% COMPLETE & TRACKING
Choose the percent_complete_method deliberately | On the Project, percent_complete_method drives the percent_complete field. Options: Manual, Task Completion, Task Progress and Task Weight — each computes progress differently.
Task Completion vs Task Progress | Task Completion counts a task as done or not (share of completed tasks); Task Progress averages each task's own progress (Percent) field for a finer-grained figure.
Task Weight for uneven tasks | The Task Weight method weights each task's contribution by its task_weight, so a large task moves the needle more than a trivial one.
Watch the via-Timesheet actuals on the Project | actual_start_date, actual_time and actual_end_date on the Project are populated from submitted Timesheets — read-only signals of what really happened versus the plan.
Enable Collect Progress if you want status updates | The collect_progress option with a frequency (Hourly / Daily / Weekly) prompts task owners for progress, feeding the Project Update trail.
ACTIVITY TYPES & RATES
Define your Activity Types | The Activity Type doctype (e.g. Development, Consulting, Support) classifies logged time; every Timesheet Detail line links to one via activity_type.
Set default costing_rate and billing_rate | Activity Type carries a Default Costing Rate and Default Billing Rate — the cost to you and the price to the client per hour for that kind of work.
Override per employee with Activity Cost | The Activity Cost doctype pins a billing_rate and costing_rate to a specific employee + activity_type pair, so a senior and a junior on the same activity bill and cost differently.
Disable rather than delete stale activities | Both Activity Type and Activity Cost expose a disabled flag — retire an old rate without breaking historical timesheets that reference it.
TIMESHEETS & BILLING
Log time on the Timesheet doctype | A Timesheet links to an employee (and user), a company and optionally a parent_project and customer; its time_logs child table (Timesheet Detail) holds the individual entries.
Capture each entry in Timesheet Detail | Each line records activity_type, from_time / to_time, hours, and the project and task it belongs to — the atomic record of who did what, when, for how long.
Mark lines is_billable to separate billable hours | The is_billable check and billing_hours split chargeable from non-chargeable time; the Timesheet totals total_hours, total_billable_hours and total_billed_hours accordingly.
Let rates flow onto each line | billing_rate and costing_rate fetch from the Activity Type / Activity Cost setup, producing billing_amount and costing_amount per line and the Timesheet's total_billable_amount and total_costing_amount.
Bill submitted timesheets into a Sales Invoice | A submitted Timesheet's billable hours can be pulled into a Sales Invoice (via the sales_invoice link); status moves Draft → Submitted → Partially Billed → Billed and per_billed tracks the share invoiced.
Tune overlap rules in Projects Settings | Projects Settings exposes ignore_user_time_overlap, ignore_employee_time_overlap and ignore_workstation_time_overlap, plus fetch_timesheet_in_sales_invoice — control how strict overlapping-time validation is.
COSTING & PROFITABILITY
Set a default Cost Center on the Project | The cost_center field ties project costs to a Cost Center for financial reporting, so project spend lands in the right slice of your accounts.
Record the estimated_costing baseline | estimated_costing (Estimated Cost) is your planned budget; total_costing_amount is the actual, rolled up from timesheet costing amounts — the two together show budget vs actual.
Read the rolled-up amount fields | The Project aggregates total_billable_amount (via Timesheet), total_billed_amount (via Sales Invoice), total_purchase_cost and total_consumed_material_cost — a full money picture without a spreadsheet.
Watch gross_margin and per_gross_margin | gross_margin and per_gross_margin (Gross Margin %) are computed on the Project from billed amount minus cost — the single number that tells you whether the engagement made money.
Reconcile task-level costing | Each Task also carries total_costing_amount and total_billing_amount (via Timesheet), so you can find which tasks eroded margin, not just which projects.
Acube Innovations · Official ERPNext Partner · acubeinnovations.com · +91 62358 66111